## Incident log
Information security incident log
ISO/IEC 27001:2022 controls 5.24 to 5.28 Incident management (with 6.8 Event reporting)
Incidents logged | 2 |  | Open | 1 |  | Major or high | 2 |  | Closed without root cause | 0 |  | Personal data involved | 1
Log during the incident, not afterwards. Times and actions written down as they happen are what make the post-incident review, the report to management and any report to the ICO or police factual rather than from memory.
Ref | Date and time reported | Reported by | How reported | What happened | Category | Severity | Incident lead | Systems or data affected | Personal data involved | Containment actions (with times) | Resolved on | Root cause | Lessons and improvements | Notified (customers, ICO, police) | Status | Notes
INC-001 | 2026-09-14 09:12 | Support inbox | Customer email | Customer reported receiving another customer's invoice by email | Data disclosure | High | Ops lead (name) | Billing system, one customer record | Yes | 09:30 email recall attempted; 09:45 recipient asked to delete and confirmed; 10:20 billing template fixed | 2026-09-14 | Mail merge field mapped to the wrong contact after a template change on 12/09 | Template changes now peer-reviewed before go-live; test send to internal address | Affected customer informed 11:00. Assessed as unlikely to result in risk; not reported to ICO, decision recorded. | Closed | EXAMPLE ROW - delete before use.
INC-002 | 2026-10-02 16:40 | J. Smith (name) | Teams message | Phishing email received by finance team; one user clicked the link and entered credentials | Account compromise | Major | IT lead (name) | One Microsoft 365 mailbox | Unknown | 16:45 password reset; 16:50 sessions revoked; 17:05 MFA methods and forwarding rules checked, one rule removed |  |  |  |  | Open | EXAMPLE ROW - delete before use. Still open: reviewing mailbox audit log for data accessed.

## Major incident roles
Major incident roles and thresholds
Decide this before you need it. Print it, and keep a copy somewhere you can reach if your own systems are down.
Role | Responsibility | Primary (name and phone) | Deputy (name and phone)
Incident lead | Owns the incident end to end. Decides severity, calls in the others, keeps the log, decides when it is closed.
Technical recovery | Contains and recovers the affected systems. Reports progress to the incident lead at agreed intervals.
Communications | Single voice to staff, customers and suppliers. Nobody else communicates externally about the incident.
Senior management | Makes business decisions: shutting systems down, paying for outside help, reporting to the ICO or police.
Scribe | Writes down what happened, who did what and when, as it happens. In a small team this is often the incident lead.
External contacts | IT support provider, cyber insurer helpline, solicitor, ICO (72 hours for reportable personal data breaches), Report Fraud (formerly Action Fraud) or police.
Severity thresholds
Severity | Example triggers | Response | Who is told
Major | Ransomware or malware spreading; confirmed compromise of an admin account; loss of a core system with no workaround; personal data breach likely to be reportable | Major incident roles activated immediately. Log opened. Updates every hour. | Senior management at once; customers and ICO as decided
High | Single account compromise; data sent to the wrong recipient; outage of a key service with a workaround | Incident lead assigned within the hour. Log opened. | Senior management same day
Medium | Lost device that was encrypted; suspicious activity contained; supplier incident with no confirmed impact on us | Handled by IT within one working day | Recorded; reported at the monthly review
Low | Phishing email reported and not clicked; blocked malware; minor policy breach | Logged and closed | Trends reported at management review

## Guidance
Guidance
What this workbook is for
Control 5.24 asks you to plan and prepare for incidents: processes, roles and responsibilities defined and communicated before anything happens. This workbook gives you the two things most small businesses are missing: a single place to log incidents, and a one-page sheet saying who does what, and at what threshold, when something serious happens.
How to use it
1. Fill in the Major incident roles tab with names and phone numbers, primary and deputy. Agree the severity thresholds and change them to suit you.
2. Delete the two example rows on the Incident log tab.
3. Log every incident, including the small ones. Trends in small incidents are often the early warning of a big one.
4. During an incident, write the containment actions with times as you go. Do not wait until it is over.
5. Do not close an incident without a root cause. The Status column flags any that were.
6. Review the log at every management review (clause 9.3) and test the plan at least once a year with a short tabletop exercise.
Reporting a personal data breach
Under UK GDPR, a personal data breach that is likely to result in a risk to individuals must be reported to the ICO without undue delay and, where feasible, within 72 hours of becoming aware of it. Record the decision either way, including when you decide not to report.
Prepared by Iseo Blue. iseoblue.com ¦ Minimal viable compliance for growing businesses.